# Sample Stakeholder Engagement Plan: Palomino ISD

# Stakeholder Engagement Example – initial engagement Student Growth Measures

## Summer 2024 – March 2025

| Month | Stakeholders | Milestones | Guiding Questions | Action Steps |
| --- | --- | --- | --- | --- |
| Summer 2024 | - District-Level Administrators | - Design and schedule general TIA information session - Host general TIA information session for all stakeholders | - What are the key areas of TIA that teachers must understand before providing input and feedback? - What parameters will we establish during the information session? - Who will be our TIA experts/ambassadors? Who has the most background knowledge and context to facilitate the session(s) and respond to questions? - How will we collect and respond to questions? - How will we differentiate information sessions for district stakeholders and campus stakeholders? | - Decide on TIA Lead - TIA Lead to develop: - General TIA information session - Key areas of TIA that need additional parameters - Host general TIA information session on August 2nd - Develop surveys and engagement sessions for the school year (subject to change) |
| September | - District-level Administrators, including assessment, curriculum and instruction - TIA Committee | - Collect district-level input on critical decisions: designation eligibility, designation criteria around student growth measures - Develop parameters before planning outreach to campus-level stakeholders. | - What growth measures are we currently using for different teaching assignments? - What evidence do we have on validity and reliability for each growth measures? - What systems are in place to support Continued validity and reliability? - What is possible with our current systems and what needs more time and training? - What limitations will we put in place before sharing information with campus-level stakeholders? - What are areas that potentially will require change management and advocacy from leadership? - How will we take into account what our surrounding districts are doing? | - Speak with District representatives about: - Student growth measures - Current growth measures in place for different teaching assignments? - Speak with other districts engaged in TIA - Plan engagement opportunities and implement: - Elementary Schools – attend PD Day at every campus and explain TIA to all teachers - Middle/High School – Attend Wednesday initial PD Day to explain TIA to all teachers - District created SGM survey - ES September 12-16th - MS/HS September 5th – 9th - Meet with admin at ES and MS/HS about growth targets September 26th – 30th - TIA Committee drafts and revises surveys to use at various points in the year using guiding questions at each step. |
| September – October | - District-level Administrators - Campus-level Administrators - Teachers in each SGM category - TIA Committee | - Which student growth measure to use for each eligible teaching assignment/ group -How student growth measures will be administered, scored, and kept secure - How individual student growth targets will be set and tracked | - What is our rationale for selecting each growth measure? - How well do our current administration and scoring practices for each growth measure align with full readiness on the system application? - How will set individual growth targets for each measure and track student progress? - What growth measures are best for each subject area/grade level? - What role will teachers have in setting student growth goals? - Do teachers have the training they need to run data reports for progress monitoring? - How will we train teachers/campus leaders/district leaders to analyze student growth data, including correlation to teacher observation data? - How will we seek input prior to proposing student growth measures for each teacher group? | - At 1st all-staff meeting: Intro to TIA video, district rationale and goals - September Principals meeting—share TIA video and present options for student growth measures and eligible assignments. Facilitate roundtable discussions and collect exit tickets. - Plan campus stakeholder engagement sessions.at staff meetings - Share TIA informational video with teachers - Share campus administrator input results, district parameters, and rationale for participating - Share possibilities for Student Growth Measures - Growth Targets for teachers - Role of teachers in system - Training needs - Collect teacher input via Panorama survey - Share initial SGM and growth targets with teachers at campus level early – October - Make adjustments based on initial feedback - Present final decisions during weekly staff meetings at both campuses at end of October - Process feedback and report to TIA committee October meeting. Begin drafting proposed Student Growth Measures for each assignment |
| November – December | - District-level Administrators - Campus-level Administrators - Teachers in each SGM category - TIA Committee | - Share first draft of Student Growth Measures component and collect feedback | - Do teachers agree that the measures are valid and reliable? - Do teachers and administrators understand what will be required of them during the data capture year if they select certain growth measures? - Do teachers understand how growth targets are set and their role in setting growth targets? | - Develop and send out survey regarding training needs to all campuses (early November) - Use survey results to plan December training sessions (given during the last two weeks of semester during weekly Wednesday PD *30 min. Max*) - TIA Committee discusses proposals with campus administrators at October admin meeting. Collect feedback via Google Forms. - Revise proposed student growth measures, process for setting growth targets. Highlight takeaways from initial stakeholder engagement surveys, changes made, rationale, and talking points for campus administrators - Campus administrators share proposals at department meetings week of November 8th - Teachers share additional feedback and questions with campus administrators by November 30th - TIA committee representatives host Q&A session/office hours Mondays throughout December |
| January – February | - District-level Administrators - Campus-level Administrators - Teachers in each SGM category - TIA Committee | - Implement Student Growth Measure component feedback and communicate changes | - If selecting new growth measures, what training is required to implement them with fidelity? - Who will lead this and when? - What is our timeline for securing/creating each assessment, if applicable? | - TIA Lead and District Leaders develop training for stakeholders (campus and teachers) for spring semester - Schedule training for all stakeholders and plan messaging – make sure to invite all stakeholders to the meetings on Google Calendar - Develop training schedule for February, March, and April (pay attention to testing dates for each campus) - Speak with campus admin to decide on training needs moving forward - Create feedback mechanisms for trainings (surveys, exit tickets, engagement activities to get information, etc.) - TIA Committee reviews all feedback and addresses questions - Committee creates final recommendation for student growth measures - Campus principals share student growth measures with faculty using slide deck Week of Feb 12th |
| March-April | - District-level Administrators submitting the TIA Application | - Submit the final TIA Application | - Prepare the district’s TIA Application for submission - Submit the final TIA Application for Cohort F | - Continue with spring semester training schedule - Continue to meet with campus level admin to clarify expectation around SGM - Hold final informational/input sessions at each campus - Prepare to share finalized plan with campuses in May (after state and local testing is complete) - Continue Q&A sessions - Share district TIA email for questions |
| Early Fall 2025 | - All Teachers | - Complete spreadsheet to submit TTU for TIA Teacher Buy-In Survey | - How do I ensure that I capture all teachers? - How can I explain the importance of completing this survey to my teachers? | - Begin compiling list of data points for submission - Create training surrounding the survey |